## Sheet1
| 2017-01-19 | 2017-01-26 | 2017-02-02 | 2017-02-09 | 2017-02-16 | 2017-02-23 | 2017-03-02 | 2017-03-09 | 2017-03-16 | 2017-03-23 | 2017-03-30 | 2017-04-06
Group Tasks
Timeline
PACT Analysis
Functional Specifications
Design Specifications
User Interface Design
ER Diagrams and database layout
HTML and CSS for Main Page
Design Main menu functions
Add customer
Delete customer
Amend customer
Search for Customer
Data validation
Prototype test, redesign and add features
End Product
Aaron
Customer front end functions
Add item to shopping cart
Delete Item from shopping cart
Amend order
Search for order
Paul
Admin back end functions
Add photograph record
Delete photograph
Amend photograph tags
Search for photograph, by date, tags, Id number